**CHEDDI JAGAN INTERNATIONAL AIRPORT CORPORATION**

**Update on 2018 Projects as at 24th January 2018**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **#** | **Particulars** | **Cost** | **Tendering** | **Schedule** | **Remarks** |
| 1 | Procurement of two (2)  4x4 Pick | 25,000,000 | Public | * Receive Quotations by 15th February * Award Contract by 31st March * Product Delivery – 1st June |  |
| 2 | One (1) Cargo Scanning Machine | 50,000,000 | Selective | * Cabinet Approval Received * Loan Agreement to sign by 15th Feb * Product Delivery – 1st July | To be sourced from Airport Equipment Manufacturer |
| 3 | Procurement of one (1) 30-seater staff bus | 20,000,000 | Public | * Receive Quotations by 1st March * Award Contract by 31st March * Product Delivery – 1st July |  |
| 4 | Construction of new Office Complex / Recreation Facility for Red Cap & Taxi / Security Building & Fencing of Compound | 50,000,000 | Public | * Advertise by 15th February * Award Contract by 15th April * Construct Facility – 1st July |  |
| 5 | Hold Baggage Scanner | 160,000,000 | Selective | * Receive Quotations by 1st March * Award Contract by 15th April * Product Delivery – 1st September | To be sourced from Airport Equipment Manufacturer |

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **#** | **Particulars** | **Cost** | **Tendering** | **Schedule** | **Remarks** |
| 6 | Cabin Baggage Scanners -3 | 48,000,000 | Selective | * Receive Quotations by 1st March * Award Contract by 31st March * Product Delivery – 1st September | To be sourced from Airport Equipment Manufacturer |
| 7 | Procure three (3) Walk Thru Metal Detectors (WTMD) | 6,000,000 | Selective | * Receive Quotations by 15th February * Award Contract by 31st March * Product Delivery – 1st June | To be sourced from Airport Equipment Manufacturer |
| 8 | Lighted Aerodrome Signs | 40,000,000 | Selective | * Receive Quotations by 1st March * Award Contract by 31st March * Product Delivery – 1st September | To be sourced from Airport Equipment Manufacturer |
| 9 | Polishers/Buffers for Airport Custodians | 4,000,000 | Public | * Receive Quotations by 15th February * Award Contract by 31st March * Product Delivery – 1st June |  |